## Product Backlog
Backlog ID | Epic / Module | Product Backlog Item | User Story | Acceptance Criteria / Definition of Done | Priority | Primary Team Stream | Owning Module | Dependencies | Requirement / Design Traceability | Story Points | Status
PB-001 | Project Foundation & User Service | Account and profile management | As a user, I want to create an account and manage my profile so that my schedule and productivity data are associated with me. | A user can register/sign in and view/update permitted profile fields; each user's records remain isolated. | P0 | Backend + Frontend | User Service | Authentication/profile design | User Service classes; security NFRs | Not estimated | Backlog
PB-002 | Project Foundation & User Service | Secure access and user data isolation | As a user, I want my personal data protected so that other users cannot access it. | Authorization is enforced on protected operations; one user cannot read or modify another user's private data. | P0 | Backend | User Service | PB-001 | Security/privacy NFRs | Not estimated | Backlog
PB-003 | Project Foundation & User Service | Core application shell and dashboard | As a user, I want a central dashboard so that I can access my schedule and productivity information. | Dashboard links to schedule, tasks, and available score/recommendation views; unavailable modules are clearly handled. | P1 | Frontend + Backend | User Service / Dashboard | PB-001 | Dashboard feature; cross-module integration | Not estimated | Backlog
PB-004 | Scheduler | Create and manage tasks | As a user, I want to create, edit, and delete tasks so that my workload stays up to date. | Task title/details and supported task fields can be saved, updated, and deleted; validation prevents invalid records. | P0 | Frontend + Backend | Scheduler | PB-001 | FR2.1 | Not estimated | Backlog
PB-005 | Scheduler | Set task attributes | As a user, I want to define task priority, deadline, estimated duration, and category so that scheduling decisions have the required inputs. | Supported attributes can be entered and edited; required fields and valid values are checked. | P0 | Frontend + Backend | Scheduler | PB-004 | FR2.2 | Not estimated | Backlog
PB-006 | Scheduler | Create fixed events and flexible tasks | As a user, I want to classify commitments as fixed or flexible so that the scheduler knows what may move. | Fixed events and flexible tasks are distinguishable; task type is persisted and used during scheduling. | P0 | Frontend + Backend | Scheduler | PB-004, PB-005 | FR2.6, FR2.11, FR2.12 | Not estimated | Backlog
PB-007 | Scheduler | Mark tasks completed or skipped | As a user, I want to mark a task completed or skipped so that the schedule reflects what happened. | Status changes are saved; completed tasks are identifiable and protected from rescheduling. | P1 | Frontend + Backend | Scheduler | PB-004 | Scheduler feature list; FR6.4 | Not estimated | Backlog
PB-008 | Scheduler | Generate an initial schedule | As a user, I want the system to generate an initial schedule so that my flexible tasks are placed into available time slots. | A schedule is generated from available tasks and fixed commitments; no overlapping scheduled items are produced. | P0 | Backend + ML/Decision support | Scheduler | PB-004, PB-005, PB-006 | FR2.3, FR2.5, FR2.6 | Not estimated | Backlog
PB-009 | Scheduler | Generate daily and weekly schedules | As a user, I want daily and weekly schedules so that I can plan both immediate and upcoming work. | The user can generate/view daily and weekly schedules using saved tasks and commitments. | P0 | Frontend + Backend | Scheduler | PB-008 | FR2.3, FR2.4 | Not estimated | Backlog
PB-010 | Scheduler | Prevent conflicts and lock fixed events | As a user, I want fixed events to remain unchanged and conflicts to be prevented so that the schedule is feasible. | Scheduled items do not overlap; fixed events are not moved by automated optimization. | P0 | Backend | Scheduler | PB-006, PB-008 | FR2.5, FR2.6, FR2.12 | Not estimated | Backlog
PB-011 | Scheduler | Recommend time slots and allocate flexible tasks | As a user, I want flexible tasks assigned to suitable available slots so that my schedule is practical. | Flexible tasks are placed only in valid available slots; fixed commitments and deadlines are respected where feasible. | P0 | Backend + ML/Decision support | Scheduler | PB-008, PB-010, Decision Engine inputs | FR2.7; FR2.6 | Not estimated | Backlog
PB-012 | Scheduler | Estimate task duration | As a user, I want the system to estimate task duration when possible so that scheduling requires less manual effort. | The system can produce a duration estimate when sufficient supported input/history exists; user-provided duration remains available. | P2 | Backend + ML | Scheduler | PB-004; historical data availability | Scheduler feature list | Not estimated | Backlog
PB-013 | Scheduler | Save schedule changes and manually rearrange tasks | As a user, I want to move tasks manually and save the changes so that I can control my plan. | Manual changes are validated, saved, and reflected in the schedule without creating conflicts. | P1 | Frontend + Backend | Scheduler | PB-008, PB-010 | FR2.8, FR2.9 | Not estimated | Backlog
PB-014 | Scheduler | Calendar views | As a user, I want daily, weekly, and monthly calendar views so that I can inspect my schedule at different levels. | Daily, weekly, and monthly views display the relevant saved schedule entries. | P1 | Frontend + Backend | Scheduler | PB-008, PB-009 | FR2.10 | Not estimated | Backlog
PB-015 | Decision Engine | Normalize decision criteria | As the system, I want decision criteria normalized so that differently scaled inputs can be compared fairly. | Supported criteria are normalized before score calculation; missing/invalid inputs are handled explicitly. | P0 | Backend + ML/Decision support | Decision Engine | PB-005, Energy and Attention data contracts | FR5.12 | Not estimated | Backlog
PB-016 | Decision Engine | Evaluate decision factors | As the system, I want to evaluate deadline, importance, energy, attention, burnout risk, duration, task type, and context so that recommendations reflect the user's situation. | The engine evaluates all defined factors using available inputs and records which inputs were considered. | P0 | Backend + ML/Decision support | Decision Engine | PB-005, PB-021, PB-025 | FR5.1, FR5.2, FR5.3, FR5.11; Decision Engine feature list | Not estimated | Backlog
PB-017 | Decision Engine | Calculate decision score and rank tasks | As the system, I want to score and rank eligible tasks so that the most suitable next task can be selected. | Criteria are normalized before scoring; tasks can be ordered by calculated score; score logic is configurable/testable. | P0 | Backend + ML/Decision support | Decision Engine | PB-015, PB-016 | FR5.1, FR5.12 | Not estimated | Backlog
PB-018 | Decision Engine | Recommend the next task or study session | As a user, I want the system to recommend the most suitable task or study session so that I know what to work on next. | A recommendation is returned from the ranked eligible tasks with its relevant task/session details. | P0 | Backend + Frontend | Decision Engine | PB-017, PB-008 | FR5.4 | Not estimated | Backlog
PB-019 | Decision Engine | Recommend breaks or postponement | As a user, I want break-time and postponement recommendations when appropriate so that I can adapt my workload. | The engine can recommend a break or postponement based on available workload, attention, priority, and related criteria. | P1 | Backend + Frontend | Decision Engine | PB-016, Attention and Energy inputs | FR5.5, FR5.6 | Not estimated | Backlog
PB-020 | Decision Engine | Explain recommendations | As a user, I want to understand why a task or action is recommended so that I can trust and evaluate the decision. | Each recommendation includes an understandable reason tied to relevant criteria; no unexplained recommendation is presented as complete. | P0 | Backend + Frontend | Decision Engine | PB-017, PB-018 | FR5.8; Explainability NFR | Not estimated | Backlog
PB-021 | Decision Engine | Re-evaluate after schedule updates | As the system, I want to reconsider decisions when the schedule changes so that recommendations remain current. | A schedule update triggers re-evaluation of affected decision inputs and refreshes recommendations when needed. | P1 | Backend | Decision Engine | PB-017, Dynamic Rescheduling integration | FR5.9 | Not estimated | Backlog
PB-022 | Decision Engine | Use history to improve future recommendations | As a user, I want future recommendations to take previous behavior and outcomes into account so that recommendations can become more personalized over time. | Relevant past decisions and user outcomes can be stored/accessed; future recommendation behavior can use this history when enough data exists. | P2 | Backend + ML | Decision Engine | PB-018; history capture | FR5.7, FR5.10 | Not estimated | Backlog
PB-023 | Energy & Burnout | Collect supported energy inputs | As a user, I want to provide or connect relevant sleep and activity information so that my energy estimate has meaningful inputs. | The system accepts the input sources actually supported by the implementation; unavailable integrations are not assumed. | P0 | Frontend + Backend | Energy & Burnout | PB-001 | FR3.1; Energy feature list | Not estimated | Backlog
PB-024 | Energy & Burnout | Calculate and classify Energy Score | As a user, I want an Energy Score and High/Medium/Low classification so that I can understand my current energy level. | A score is calculated from supported sleep, workload, and activity inputs and mapped to a documented level. | P0 | Backend + ML | Energy & Burnout | PB-023 | FR3.1, FR3.3 | Not estimated | Backlog
PB-025 | Energy & Burnout | Track energy history, fatigue, and recovery | As a user, I want historical energy records and fatigue/recovery estimates so that I can see patterns over time. | Energy history is saved; fatigue and recovery outputs are generated only according to defined project logic. | P1 | Backend + ML | Energy & Burnout | PB-024 | FR3.7, FR3.11, FR3.12 | Not estimated | Backlog
PB-026 | Energy & Burnout | Identify productive hours and task intensity | As a user, I want energy-aware task intensity and productive-hour guidance so that tasks fit my current state. | The system can provide intensity guidance and productive-hour estimates from available data; recommendations are exposed to scheduling. | P1 | Backend + ML + Frontend | Energy & Burnout | PB-024, PB-025 | FR3.4, FR3.13; Energy feature list | Not estimated | Backlog
PB-027 | Energy & Burnout | Update score and notify critical low energy | As a user, I want my Energy Score to update when new information arrives and be notified when it is critically low. | New supported inputs trigger an update; critical-low notification follows a documented rule; update target is <=1 second where applicable. | P1 | Backend + Frontend | Energy & Burnout | PB-024, notifications capability | FR3.2, FR3.5, FR3.10; real-time NFR | Not estimated | Backlog
PB-028 | Energy & Burnout | Dashboard and weekly energy report | As a user, I want to see my current score and weekly trends so that I can monitor changes. | Current score is displayed; weekly report summarizes available historical records. | P2 | Frontend + Backend | Energy & Burnout / Dashboard | PB-025 | FR3.6, FR3.8 | Not estimated | Backlog
PB-029 | Attention | Collect attention signals | As a user, I want the system to use supported screen-time and behavioral signals so that attention can be estimated. | The system records/consumes only permitted, available signals; data collection follows privacy and consent requirements. | P0 | Backend + Frontend | Attention | PB-001; platform data access feasibility | FR4.2, FR4.11 | Not estimated | Backlog
PB-030 | Attention | Calculate and classify Attention Score | As a user, I want an Attention Score and High/Medium/Low classification so that I can understand my focus state. | A score is calculated from available behavioral/activity signals and mapped to a documented level. | P0 | Backend + ML | Attention | PB-029 | FR4.1, FR4.3 | Not estimated | Backlog
PB-031 | Attention | Detect drops, distraction, and prolonged focus | As a user, I want the system to detect declining attention or prolonged focus so that it can suggest an appropriate response. | The system detects configured patterns from available signals; rules/thresholds are documented and configurable. | P1 | Backend + ML | Attention | PB-030 | FR4.6, FR4.12; Attention feature list | Not estimated | Backlog
PB-032 | Attention | Recommend focus sessions and breaks | As a user, I want focus-session length and break recommendations suited to my attention level so that work sessions remain realistic. | Recommendations use current attention and task priority; focus sessions can be shortened when attention drops significantly. | P1 | Backend + Frontend | Attention | PB-030, PB-031 | FR4.4, FR4.5, FR4.12 | Not estimated | Backlog
PB-033 | Attention | Attention history and trends | As a user, I want daily and weekly attention trends so that I can understand my focus patterns. | Historical attention records are saved and daily/weekly trends can be displayed. | P2 | Backend + Frontend | Attention | PB-030 | FR4.7, FR4.8 | Not estimated | Backlog
PB-034 | Attention | Update recommendations when attention changes | As the system, I want recommendations to refresh when attention changes so that scheduling remains aligned with the user's state. | A relevant score change triggers downstream recommendation refresh; target update latency is <=1 second where applicable. | P1 | Backend | Attention | PB-030, Decision Engine integration | FR4.9, FR4.10; real-time NFR | Not estimated | Backlog
PB-035 | Dynamic Rescheduling | Detect schedule-changing events | As the system, I want to detect new tasks/events, deadline changes, missed tasks, and conflicts so that the schedule can be repaired. | Each supported change type triggers a rescheduling evaluation and affected items are identified. | P0 | Backend | Dynamic Rescheduling | PB-004, PB-006, PB-008 | FR6.1, FR6.2, FR6.3; Dynamic Rescheduling feature list | Not estimated | Backlog
PB-036 | Dynamic Rescheduling | Recalculate affected flexible tasks | As a user, I want the system to repair the schedule after a change while preserving fixed commitments and completed tasks. | Fixed and completed items remain unchanged; only necessary flexible tasks are moved; flexible-task reorder target <=2 seconds. | P0 | Backend + Decision support | Dynamic Rescheduling | PB-035, PB-010, PB-017 | FR6.4, FR6.5, FR6.8; latency NFR | Not estimated | Backlog
PB-037 | Dynamic Rescheduling | Preview and confirm major schedule changes | As a user, I want to review and accept or reject major schedule changes so that I remain in control. | Major changes require user confirmation; the user can accept or reject the proposal; rejected proposals do not replace the active schedule. | P1 | Frontend + Backend | Dynamic Rescheduling | PB-036 | FR6.6, FR6.7 | Not estimated | Backlog
PB-038 | Dynamic Rescheduling | Apply changes and update dependent notifications | As a user, I want accepted schedule changes and reminders to stay synchronized so that I do not receive outdated notifications. | Accepted changes update the active schedule and dependent reminders; schedule regeneration occurs after accepted modifications. | P1 | Backend + Frontend | Dynamic Rescheduling | PB-037, notification capability | FR6.9, FR6.10 | Not estimated | Backlog
PB-039 | Calendar & Email Parsing | Connect external calendar securely | As a user, I want to connect a supported calendar so that existing commitments can be considered in my schedule. | Only explicitly supported providers are offered; authorization is secure and can be revoked; imported events are associated with the correct user. | P1 | Backend + Frontend | Calendar & Email Parsing | PB-001; provider selection | OAuth2 security NFR | Not estimated | Backlog
PB-040 | Calendar & Email Parsing | Parse calendar/email data into events | As a user, I want supported calendar/email information extracted into events so that I can reduce manual entry. | Supported source data is parsed into structured events; parsing failures are visible; background email parsing target <=5 seconds where applicable. | P2 | Backend + ML/NLP | Calendar & Email Parsing | PB-039; provider/API feasibility | Email parsing feature; latency NFR | Not estimated | Backlog
PB-041 | Calendar & Email Parsing | Review imported events before task creation | As a user, I want imported event details reviewed or validated before they affect my schedule so that incorrect extraction does not silently corrupt my plan. | Imported events can be inspected; event and task concepts remain distinct; only valid/confirmed data enters scheduling. | P2 | Frontend + Backend | Calendar & Email Parsing / Scheduler | PB-040, PB-006 | Event-to-Task flow in architecture | Not estimated | Backlog
PB-042 | Notifications & Integration | Deliver relevant reminders and alerts | As a user, I want reminders for schedule items and important score/rescheduling events so that I can act at the right time. | Notifications are generated from supported triggers and reflect the current schedule; obsolete reminders are updated or cancelled. | P1 | Backend + Frontend | Cross-module | PB-008, PB-027, PB-038 | FR6.9; Energy critical-low feature | Not estimated | Backlog
PB-043 | AI/ML Evaluation | Establish baseline and evaluate intelligent components | As the project team, we want to evaluate score/prediction/recommendation components so that their behavior can be assessed rather than assumed. | Evaluation data/criteria are documented; metrics are chosen to match each implemented component; no performance claim is made without measured results. | P1 | ML + Backend | Cross-module / ML | At least one ML/decision component implemented | Project evaluation; model validation | Not estimated | Backlog
PB-044 | Quality & Security | Meet privacy, security, and performance requirements | As a user, I want sensitive behavioral, screen-time, and email data protected and key operations responsive so that the system is safe and usable. | Sensitive data is protected in transit/at rest as applicable; performance is measured against specified targets; results and gaps are documented. | P0 | Backend + Frontend + ML | Cross-module | Security architecture and integrations | NFR: encryption; <=1s score updates; <=2s flexible rescheduling; <=5s email parsing; >=99.5% availability | Not estimated | Backlog
PB-045 | Quality & Security | Support offline viewing and later synchronization where feasible | As a user, I want access to my last saved schedule when offline so that I can still consult my plan. | Last saved schedule/calendar data is available locally where supported; changes synchronize on reconnect with conflict handling documented. | P2 | Frontend + Backend | Cross-module / Scheduler | PB-008, local persistence approach | Offline NFR | Not estimated | Backlog
PB-046 | Integration & Deployment | Integrate modules and validate end-to-end workflows | As a user, I want the modules to work together so that changes in tasks, energy, attention, and events produce coherent scheduling outcomes. | Core end-to-end scenarios pass; module contracts are consistent; errors and integration gaps are documented. | P0 | Frontend + Backend + ML | Cross-module | Core modules implemented | Master Class Diagram cross-service contracts | Not estimated | Backlog
PB-047 | Testing & Release | Run functional, integration, usability, and performance testing | As the project team, we want to test the system systematically so that defects and requirement gaps are identified before submission. | Test cases map to requirements; critical flows are tested; performance/security findings and unresolved issues are recorded. | P0 | Frontend + Backend + ML | Cross-module | PB-046 | FR/NFR traceability | Not estimated | Backlog
PB-048 | Documentation & Delivery | Prepare technical documentation and final demo | As the project team, we want complete documentation and a reproducible demonstration so that the project can be evaluated and maintained. | Report includes the approved chapters and diagrams; setup instructions and demo scenarios are available; no unimplemented capability is described as completed. | P0 | All team members | Cross-module | Implementation and test evidence | Academic submission and demo | Not estimated | Backlog

## Read Me
Topic | Guidance
Purpose | Initial Product Backlog for the AI-Assisted Personal Scheduler / Productivity Planner. It is a living Agile artifact, not a fixed Sprint Plan.
Planning horizon | Project deadline is around May 2027. Sprints are two weeks. Sprint assignment is intentionally not fixed in this file; select items during Sprint Planning based on priority, dependencies, and team capacity.
Team streams | Frontend, Backend, and ML. A backlog item may require collaboration across streams; the Primary Team Stream column is a starting point, not a restriction.
Priority | P0 = foundational / critical path; P1 = important after foundations; P2 = advanced or dependent capability. Revisit with the Product Owner / supervisor.
Estimation | Story Points are left as 'Not estimated' because the team must estimate collaboratively (e.g., Planning Poker). Do not treat these as hours.
Status | All entries start in Backlog. Update status during refinement and sprint execution.
Requirements traceability | FR references are included where they are explicitly known from the available project context. Some entries point to feature lists or NFR descriptions where a precise requirement ID was not available; do not invent IDs.
Scope caution | Calendar/email integration and offline support are retained as planned capabilities from the wider project context, but their implementation feasibility/provider scope should be confirmed before committing them to a Sprint.
ML caution | The backlog does not force an ML model/algorithm that has not been finalized. Define and evaluate algorithms in the ML workstream, then connect outputs through agreed module contracts.
UML status | UML is considered complete. This backlog uses the existing module boundaries and does not add UML work.

## Coverage Map
Module / Area | Feature Coverage Summary | Backlog Items
Scheduler | Create/edit/delete tasks; completed/skipped status; fixed/flexible; category/priority/deadline/duration; initial/daily/weekly schedule; conflicts; fixed lock; flexible allocation; duration estimate; save/manual rearrangement; daily/weekly/monthly views | PB-004–PB-014
Decision Engine | Normalize criteria; evaluate deadline/importance/energy/attention/burnout/duration/type/context; score/rank/select; task/study/break/postpone recommendations; explanations; reevaluation; learning from history | PB-015–PB-022
Energy & Burnout | Sleep/activity/workload inputs; score and level; history; fatigue/recovery; task intensity; productive hours; updates/critical alert; dashboard/weekly report | PB-023–PB-028
Attention | Screen time/behavior logs; score/level; detect drops/prolonged focus/distraction; focus and break recommendations; history/trends; update recommendations | PB-029–PB-034
Dynamic Rescheduling | Detect new tasks/events/deadline changes/missed tasks/conflicts; repair schedule; preserve fixed/completed; minimize changes; confirm major changes; sync order/reminders; apply accepted plan | PB-035–PB-038
Calendar & Email Parsing | Secure calendar connection; parse supported email/calendar inputs; event review and controlled task creation | PB-039–PB-041
User Service / Dashboard / Notifications | Accounts/profile; user data isolation; dashboard; reminders and alerts | PB-001–PB-003, PB-042
Quality / ML / Delivery | Evaluate intelligent components; security/performance; offline access if feasible; integration; testing; documentation/demo | PB-043–PB-048