## Sprint Roadmap
Sprint | Sprint Focus | Duration | Sprint Goal | Backlog Items | P0 | P1 | P2 | Modules | Team Participation
S01 | Foundation & Core Setup | 2 weeks | Establish the minimum foundation and input paths required by the core scheduling and score modules. | PB-001, PB-002, PB-004, PB-005, PB-023, PB-029 | 6 | 0 | 0 | Attention; Energy & Burnout; Scheduler; User Service | Frontend + Backend + ML participate where the selected backlog items require their stream.
S02 | Scheduler Core | 2 weeks | Build core task handling and initial schedule generation with fixed/flexible behavior and conflict prevention. | PB-006, PB-007, PB-008, PB-010 | 3 | 1 | 0 | Scheduler | Frontend + Backend + ML participate where the selected backlog items require their stream.
S03 | Schedule Views & Interaction | 2 weeks | Make generated schedules usable through calendar views, manual changes, and flexible-task allocation. | PB-009, PB-013, PB-014, PB-011 | 2 | 2 | 0 | Scheduler | Frontend + Backend + ML participate where the selected backlog items require their stream.
S04 | Energy Score | 2 weeks | Deliver Energy Score, classification, history/fatigue/recovery, intensity/productive-hour guidance, and updates. | PB-024, PB-025, PB-026, PB-027 | 1 | 3 | 0 | Energy & Burnout | Frontend + Backend + ML participate where the selected backlog items require their stream.
S05 | Attention Score | 2 weeks | Deliver Attention Score, detection, focus/break recommendations, history/trends, and recommendation updates. | PB-030, PB-031, PB-032, PB-033, PB-034 | 1 | 3 | 1 | Attention | Frontend + Backend + ML participate where the selected backlog items require their stream.
S06 | Decision Engine Core | 2 weeks | Build normalization, factor evaluation, decision scoring, and task ranking. | PB-015, PB-016, PB-017 | 3 | 0 | 0 | Decision Engine | Frontend + Backend + ML participate where the selected backlog items require their stream.
S07 | Recommendations & Explainability | 2 weeks | Turn ranked decisions into actionable recommendations and understandable explanations. | PB-018, PB-019, PB-020 | 2 | 1 | 0 | Decision Engine | Frontend + Backend + ML participate where the selected backlog items require their stream.
S08 | Dynamic Rescheduling Core | 2 weeks | Detect schedule changes and perform minimal repair while preserving fixed and completed work. | PB-035, PB-036 | 2 | 0 | 0 | Dynamic Rescheduling | Frontend + Backend + ML participate where the selected backlog items require their stream.
S09 | Rescheduling Control & Sync | 2 weeks | Connect re-evaluation, user confirmation, schedule application, and notification synchronization. | PB-021, PB-037, PB-038, PB-042 | 0 | 4 | 0 | Cross-module; Decision Engine; Dynamic Rescheduling | Frontend + Backend + ML participate where the selected backlog items require their stream.
S10 | Calendar & Email Integration | 2 weeks | Add supported external calendar/email ingestion and controlled event-to-scheduling flow. | PB-039, PB-040, PB-041 | 0 | 1 | 2 | Calendar & Email Parsing; Calendar & Email Parsing / Scheduler | Frontend + Backend + ML participate where the selected backlog items require their stream.
S11 | Personalization & Advanced Intelligence | 2 weeks | Add duration estimation, history-based recommendation improvement, and energy dashboard/reporting. | PB-012, PB-022, PB-028 | 0 | 0 | 3 | Decision Engine; Energy & Burnout / Dashboard; Scheduler | Frontend + Backend + ML participate where the selected backlog items require their stream.
S12 | Dashboard & Cross-Module Integration | 2 weeks | Bring the main user-facing information together and validate end-to-end interactions. | PB-003, PB-046 | 1 | 1 | 0 | Cross-module; User Service / Dashboard | Frontend + Backend + ML participate where the selected backlog items require their stream.
S13 | Quality, Security & Evaluation | 2 weeks | Evaluate intelligent components and validate security, performance, offline behavior where supported, and system quality. | PB-043, PB-044, PB-045, PB-047 | 2 | 1 | 1 | Cross-module; Cross-module / ML; Cross-module / Scheduler | Frontend + Backend + ML participate where the selected backlog items require their stream.
S14 | Final Stabilization & Delivery | 2 weeks | Final integration, defect resolution, testing evidence, documentation, and demonstration readiness. | PB-046, PB-047, PB-048 | 3 | 0 | 0 | Cross-module | Frontend + Backend + ML participate where the selected backlog items require their stream.

## Sprint Backlog
Sprint | Sprint Focus | Backlog ID | Backlog Item | Priority | Primary Team Stream | Owning Module | Dependencies | Traceability | Acceptance Criteria / Definition of Done | Story Points | Status
S01 | Foundation & Core Setup | PB-001 | Account and profile management | P0 | Backend + Frontend | User Service | Authentication/profile design | User Service classes; security NFRs | A user can register/sign in and view/update permitted profile fields; each user's records remain isolated. | Team estimate | Planned
S01 | Foundation & Core Setup | PB-002 | Secure access and user data isolation | P0 | Backend | User Service | PB-001 | Security/privacy NFRs | Authorization is enforced on protected operations; one user cannot read or modify another user's private data. | Team estimate | Planned
S01 | Foundation & Core Setup | PB-004 | Create and manage tasks | P0 | Frontend + Backend | Scheduler | PB-001 | FR2.1 | Task title/details and supported task fields can be saved, updated, and deleted; validation prevents invalid records. | Team estimate | Planned
S01 | Foundation & Core Setup | PB-005 | Set task attributes | P0 | Frontend + Backend | Scheduler | PB-004 | FR2.2 | Supported attributes can be entered and edited; required fields and valid values are checked. | Team estimate | Planned
S01 | Foundation & Core Setup | PB-023 | Collect supported energy inputs | P0 | Frontend + Backend | Energy & Burnout | PB-001 | FR3.1; Energy feature list | The system accepts the input sources actually supported by the implementation; unavailable integrations are not assumed. | Team estimate | Planned
S01 | Foundation & Core Setup | PB-029 | Collect attention signals | P0 | Backend + Frontend | Attention | PB-001; platform data access feasibility | FR4.2, FR4.11 | The system records/consumes only permitted, available signals; data collection follows privacy and consent requirements. | Team estimate | Planned
S02 | Scheduler Core | PB-006 | Create fixed events and flexible tasks | P0 | Frontend + Backend | Scheduler | PB-004, PB-005 | FR2.6, FR2.11, FR2.12 | Fixed events and flexible tasks are distinguishable; task type is persisted and used during scheduling. | Team estimate | Planned
S02 | Scheduler Core | PB-007 | Mark tasks completed or skipped | P1 | Frontend + Backend | Scheduler | PB-004 | Scheduler feature list; FR6.4 | Status changes are saved; completed tasks are identifiable and protected from rescheduling. | Team estimate | Planned
S02 | Scheduler Core | PB-008 | Generate an initial schedule | P0 | Backend + ML/Decision support | Scheduler | PB-004, PB-005, PB-006 | FR2.3, FR2.5, FR2.6 | A schedule is generated from available tasks and fixed commitments; no overlapping scheduled items are produced. | Team estimate | Planned
S02 | Scheduler Core | PB-010 | Prevent conflicts and lock fixed events | P0 | Backend | Scheduler | PB-006, PB-008 | FR2.5, FR2.6, FR2.12 | Scheduled items do not overlap; fixed events are not moved by automated optimization. | Team estimate | Planned
S03 | Schedule Views & Interaction | PB-009 | Generate daily and weekly schedules | P0 | Frontend + Backend | Scheduler | PB-008 | FR2.3, FR2.4 | The user can generate/view daily and weekly schedules using saved tasks and commitments. | Team estimate | Planned
S03 | Schedule Views & Interaction | PB-013 | Save schedule changes and manually rearrange tasks | P1 | Frontend + Backend | Scheduler | PB-008, PB-010 | FR2.8, FR2.9 | Manual changes are validated, saved, and reflected in the schedule without creating conflicts. | Team estimate | Planned
S03 | Schedule Views & Interaction | PB-014 | Calendar views | P1 | Frontend + Backend | Scheduler | PB-008, PB-009 | FR2.10 | Daily, weekly, and monthly views display the relevant saved schedule entries. | Team estimate | Planned
S03 | Schedule Views & Interaction | PB-011 | Recommend time slots and allocate flexible tasks | P0 | Backend + ML/Decision support | Scheduler | PB-008, PB-010, Decision Engine inputs | FR2.7; FR2.6 | Flexible tasks are placed only in valid available slots; fixed commitments and deadlines are respected where feasible. | Team estimate | Planned
S04 | Energy Score | PB-024 | Calculate and classify Energy Score | P0 | Backend + ML | Energy & Burnout | PB-023 | FR3.1, FR3.3 | A score is calculated from supported sleep, workload, and activity inputs and mapped to a documented level. | Team estimate | Planned
S04 | Energy Score | PB-025 | Track energy history, fatigue, and recovery | P1 | Backend + ML | Energy & Burnout | PB-024 | FR3.7, FR3.11, FR3.12 | Energy history is saved; fatigue and recovery outputs are generated only according to defined project logic. | Team estimate | Planned
S04 | Energy Score | PB-026 | Identify productive hours and task intensity | P1 | Backend + ML + Frontend | Energy & Burnout | PB-024, PB-025 | FR3.4, FR3.13; Energy feature list | The system can provide intensity guidance and productive-hour estimates from available data; recommendations are exposed to scheduling. | Team estimate | Planned
S04 | Energy Score | PB-027 | Update score and notify critical low energy | P1 | Backend + Frontend | Energy & Burnout | PB-024, notifications capability | FR3.2, FR3.5, FR3.10; real-time NFR | New supported inputs trigger an update; critical-low notification follows a documented rule; update target is <=1 second where applicable. | Team estimate | Planned
S05 | Attention Score | PB-030 | Calculate and classify Attention Score | P0 | Backend + ML | Attention | PB-029 | FR4.1, FR4.3 | A score is calculated from available behavioral/activity signals and mapped to a documented level. | Team estimate | Planned
S05 | Attention Score | PB-031 | Detect drops, distraction, and prolonged focus | P1 | Backend + ML | Attention | PB-030 | FR4.6, FR4.12; Attention feature list | The system detects configured patterns from available signals; rules/thresholds are documented and configurable. | Team estimate | Planned
S05 | Attention Score | PB-032 | Recommend focus sessions and breaks | P1 | Backend + Frontend | Attention | PB-030, PB-031 | FR4.4, FR4.5, FR4.12 | Recommendations use current attention and task priority; focus sessions can be shortened when attention drops significantly. | Team estimate | Planned
S05 | Attention Score | PB-033 | Attention history and trends | P2 | Backend + Frontend | Attention | PB-030 | FR4.7, FR4.8 | Historical attention records are saved and daily/weekly trends can be displayed. | Team estimate | Planned
S05 | Attention Score | PB-034 | Update recommendations when attention changes | P1 | Backend | Attention | PB-030, Decision Engine integration | FR4.9, FR4.10; real-time NFR | A relevant score change triggers downstream recommendation refresh; target update latency is <=1 second where applicable. | Team estimate | Planned
S06 | Decision Engine Core | PB-015 | Normalize decision criteria | P0 | Backend + ML/Decision support | Decision Engine | PB-005, Energy and Attention data contracts | FR5.12 | Supported criteria are normalized before score calculation; missing/invalid inputs are handled explicitly. | Team estimate | Planned
S06 | Decision Engine Core | PB-016 | Evaluate decision factors | P0 | Backend + ML/Decision support | Decision Engine | PB-005, PB-021, PB-025 | FR5.1, FR5.2, FR5.3, FR5.11; Decision Engine feature list | The engine evaluates all defined factors using available inputs and records which inputs were considered. | Team estimate | Planned
S06 | Decision Engine Core | PB-017 | Calculate decision score and rank tasks | P0 | Backend + ML/Decision support | Decision Engine | PB-015, PB-016 | FR5.1, FR5.12 | Criteria are normalized before scoring; tasks can be ordered by calculated score; score logic is configurable/testable. | Team estimate | Planned
S07 | Recommendations & Explainability | PB-018 | Recommend the next task or study session | P0 | Backend + Frontend | Decision Engine | PB-017, PB-008 | FR5.4 | A recommendation is returned from the ranked eligible tasks with its relevant task/session details. | Team estimate | Planned
S07 | Recommendations & Explainability | PB-019 | Recommend breaks or postponement | P1 | Backend + Frontend | Decision Engine | PB-016, Attention and Energy inputs | FR5.5, FR5.6 | The engine can recommend a break or postponement based on available workload, attention, priority, and related criteria. | Team estimate | Planned
S07 | Recommendations & Explainability | PB-020 | Explain recommendations | P0 | Backend + Frontend | Decision Engine | PB-017, PB-018 | FR5.8; Explainability NFR | Each recommendation includes an understandable reason tied to relevant criteria; no unexplained recommendation is presented as complete. | Team estimate | Planned
S08 | Dynamic Rescheduling Core | PB-035 | Detect schedule-changing events | P0 | Backend | Dynamic Rescheduling | PB-004, PB-006, PB-008 | FR6.1, FR6.2, FR6.3; Dynamic Rescheduling feature list | Each supported change type triggers a rescheduling evaluation and affected items are identified. | Team estimate | Planned
S08 | Dynamic Rescheduling Core | PB-036 | Recalculate affected flexible tasks | P0 | Backend + Decision support | Dynamic Rescheduling | PB-035, PB-010, PB-017 | FR6.4, FR6.5, FR6.8; latency NFR | Fixed and completed items remain unchanged; only necessary flexible tasks are moved; flexible-task reorder target <=2 seconds. | Team estimate | Planned
S09 | Rescheduling Control & Sync | PB-021 | Re-evaluate after schedule updates | P1 | Backend | Decision Engine | PB-017, Dynamic Rescheduling integration | FR5.9 | A schedule update triggers re-evaluation of affected decision inputs and refreshes recommendations when needed. | Team estimate | Planned
S09 | Rescheduling Control & Sync | PB-037 | Preview and confirm major schedule changes | P1 | Frontend + Backend | Dynamic Rescheduling | PB-036 | FR6.6, FR6.7 | Major changes require user confirmation; the user can accept or reject the proposal; rejected proposals do not replace the active schedule. | Team estimate | Planned
S09 | Rescheduling Control & Sync | PB-038 | Apply changes and update dependent notifications | P1 | Backend + Frontend | Dynamic Rescheduling | PB-037, notification capability | FR6.9, FR6.10 | Accepted changes update the active schedule and dependent reminders; schedule regeneration occurs after accepted modifications. | Team estimate | Planned
S09 | Rescheduling Control & Sync | PB-042 | Deliver relevant reminders and alerts | P1 | Backend + Frontend | Cross-module | PB-008, PB-027, PB-038 | FR6.9; Energy critical-low feature | Notifications are generated from supported triggers and reflect the current schedule; obsolete reminders are updated or cancelled. | Team estimate | Planned
S10 | Calendar & Email Integration | PB-039 | Connect external calendar securely | P1 | Backend + Frontend | Calendar & Email Parsing | PB-001; provider selection | OAuth2 security NFR | Only explicitly supported providers are offered; authorization is secure and can be revoked; imported events are associated with the correct user. | Team estimate | Planned
S10 | Calendar & Email Integration | PB-040 | Parse calendar/email data into events | P2 | Backend + ML/NLP | Calendar & Email Parsing | PB-039; provider/API feasibility | Email parsing feature; latency NFR | Supported source data is parsed into structured events; parsing failures are visible; background email parsing target <=5 seconds where applicable. | Team estimate | Planned
S10 | Calendar & Email Integration | PB-041 | Review imported events before task creation | P2 | Frontend + Backend | Calendar & Email Parsing / Scheduler | PB-040, PB-006 | Event-to-Task flow in architecture | Imported events can be inspected; event and task concepts remain distinct; only valid/confirmed data enters scheduling. | Team estimate | Planned
S11 | Personalization & Advanced Intelligence | PB-012 | Estimate task duration | P2 | Backend + ML | Scheduler | PB-004; historical data availability | Scheduler feature list | The system can produce a duration estimate when sufficient supported input/history exists; user-provided duration remains available. | Team estimate | Planned
S11 | Personalization & Advanced Intelligence | PB-022 | Use history to improve future recommendations | P2 | Backend + ML | Decision Engine | PB-018; history capture | FR5.7, FR5.10 | Relevant past decisions and user outcomes can be stored/accessed; future recommendation behavior can use this history when enough data exists. | Team estimate | Planned
S11 | Personalization & Advanced Intelligence | PB-028 | Dashboard and weekly energy report | P2 | Frontend + Backend | Energy & Burnout / Dashboard | PB-025 | FR3.6, FR3.8 | Current score is displayed; weekly report summarizes available historical records. | Team estimate | Planned
S12 | Dashboard & Cross-Module Integration | PB-003 | Core application shell and dashboard | P1 | Frontend + Backend | User Service / Dashboard | PB-001 | Dashboard feature; cross-module integration | Dashboard links to schedule, tasks, and available score/recommendation views; unavailable modules are clearly handled. | Team estimate | Planned
S12 | Dashboard & Cross-Module Integration | PB-046 | Integrate modules and validate end-to-end workflows | P0 | Frontend + Backend + ML | Cross-module | Core modules implemented | Master Class Diagram cross-service contracts | Core end-to-end scenarios pass; module contracts are consistent; errors and integration gaps are documented. | Team estimate | Planned
S13 | Quality, Security & Evaluation | PB-043 | Establish baseline and evaluate intelligent components | P1 | ML + Backend | Cross-module / ML | At least one ML/decision component implemented | Project evaluation; model validation | Evaluation data/criteria are documented; metrics are chosen to match each implemented component; no performance claim is made without measured results. | Team estimate | Planned
S13 | Quality, Security & Evaluation | PB-044 | Meet privacy, security, and performance requirements | P0 | Backend + Frontend + ML | Cross-module | Security architecture and integrations | NFR: encryption; <=1s score updates; <=2s flexible rescheduling; <=5s email parsing; >=99.5% availability | Sensitive data is protected in transit/at rest as applicable; performance is measured against specified targets; results and gaps are documented. | Team estimate | Planned
S13 | Quality, Security & Evaluation | PB-045 | Support offline viewing and later synchronization where feasible | P2 | Frontend + Backend | Cross-module / Scheduler | PB-008, local persistence approach | Offline NFR | Last saved schedule/calendar data is available locally where supported; changes synchronize on reconnect with conflict handling documented. | Team estimate | Planned
S13 | Quality, Security & Evaluation | PB-047 | Run functional, integration, usability, and performance testing | P0 | Frontend + Backend + ML | Cross-module | PB-046 | FR/NFR traceability | Test cases map to requirements; critical flows are tested; performance/security findings and unresolved issues are recorded. | Team estimate | Planned
S14 | Final Stabilization & Delivery | PB-046 | Integrate modules and validate end-to-end workflows | P0 | Frontend + Backend + ML | Cross-module | Core modules implemented | Master Class Diagram cross-service contracts | Core end-to-end scenarios pass; module contracts are consistent; errors and integration gaps are documented. | Team estimate | Planned
S14 | Final Stabilization & Delivery | PB-047 | Run functional, integration, usability, and performance testing | P0 | Frontend + Backend + ML | Cross-module | PB-046 | FR/NFR traceability | Test cases map to requirements; critical flows are tested; performance/security findings and unresolved issues are recorded. | Team estimate | Planned
S14 | Final Stabilization & Delivery | PB-048 | Prepare technical documentation and final demo | P0 | All team members | Cross-module | Implementation and test evidence | Academic submission and demo | Report includes the approved chapters and diagrams; setup instructions and demo scenarios are available; no unimplemented capability is described as completed. | Team estimate | Planned

## Team Lanes
Sprint | Sprint Focus | Team Lane | Backlog IDs | Work Scope from Backlog
S01 | Foundation & Core Setup | Frontend | PB-001, PB-004, PB-005, PB-023, PB-029 | Account and profile management; Create and manage tasks; Set task attributes; Collect supported energy inputs; Collect attention signals
S01 | Foundation & Core Setup | Backend | PB-001, PB-002, PB-004, PB-005, PB-023, PB-029 | Account and profile management; Secure access and user data isolation; Create and manage tasks; Set task attributes; Collect supported energy inputs; Collect attention signals
S02 | Scheduler Core | Frontend | PB-006, PB-007 | Create fixed events and flexible tasks; Mark tasks completed or skipped
S02 | Scheduler Core | Backend | PB-006, PB-007, PB-008, PB-010 | Create fixed events and flexible tasks; Mark tasks completed or skipped; Generate an initial schedule; Prevent conflicts and lock fixed events
S02 | Scheduler Core | ML | PB-008 | Generate an initial schedule
S03 | Schedule Views & Interaction | Frontend | PB-009, PB-013, PB-014 | Generate daily and weekly schedules; Save schedule changes and manually rearrange tasks; Calendar views
S03 | Schedule Views & Interaction | Backend | PB-009, PB-013, PB-014, PB-011 | Generate daily and weekly schedules; Save schedule changes and manually rearrange tasks; Calendar views; Recommend time slots and allocate flexible tasks
S03 | Schedule Views & Interaction | ML | PB-011 | Recommend time slots and allocate flexible tasks
S04 | Energy Score | Frontend | PB-026, PB-027 | Identify productive hours and task intensity; Update score and notify critical low energy
S04 | Energy Score | Backend | PB-024, PB-025, PB-026, PB-027 | Calculate and classify Energy Score; Track energy history, fatigue, and recovery; Identify productive hours and task intensity; Update score and notify critical low energy
S04 | Energy Score | ML | PB-024, PB-025, PB-026 | Calculate and classify Energy Score; Track energy history, fatigue, and recovery; Identify productive hours and task intensity
S05 | Attention Score | Frontend | PB-032, PB-033 | Recommend focus sessions and breaks; Attention history and trends
S05 | Attention Score | Backend | PB-030, PB-031, PB-032, PB-033, PB-034 | Calculate and classify Attention Score; Detect drops, distraction, and prolonged focus; Recommend focus sessions and breaks; Attention history and trends; Update recommendations when attention changes
S05 | Attention Score | ML | PB-030, PB-031 | Calculate and classify Attention Score; Detect drops, distraction, and prolonged focus
S06 | Decision Engine Core | Backend | PB-015, PB-016, PB-017 | Normalize decision criteria; Evaluate decision factors; Calculate decision score and rank tasks
S06 | Decision Engine Core | ML | PB-015, PB-016, PB-017 | Normalize decision criteria; Evaluate decision factors; Calculate decision score and rank tasks
S07 | Recommendations & Explainability | Frontend | PB-018, PB-019, PB-020 | Recommend the next task or study session; Recommend breaks or postponement; Explain recommendations
S07 | Recommendations & Explainability | Backend | PB-018, PB-019, PB-020 | Recommend the next task or study session; Recommend breaks or postponement; Explain recommendations
S08 | Dynamic Rescheduling Core | Backend | PB-035, PB-036 | Detect schedule-changing events; Recalculate affected flexible tasks
S08 | Dynamic Rescheduling Core | ML | PB-036 | Recalculate affected flexible tasks
S09 | Rescheduling Control & Sync | Frontend | PB-037, PB-038, PB-042 | Preview and confirm major schedule changes; Apply changes and update dependent notifications; Deliver relevant reminders and alerts
S09 | Rescheduling Control & Sync | Backend | PB-021, PB-037, PB-038, PB-042 | Re-evaluate after schedule updates; Preview and confirm major schedule changes; Apply changes and update dependent notifications; Deliver relevant reminders and alerts
S10 | Calendar & Email Integration | Frontend | PB-039, PB-041 | Connect external calendar securely; Review imported events before task creation
S10 | Calendar & Email Integration | Backend | PB-039, PB-040, PB-041 | Connect external calendar securely; Parse calendar/email data into events; Review imported events before task creation
S10 | Calendar & Email Integration | ML | PB-040 | Parse calendar/email data into events
S11 | Personalization & Advanced Intelligence | Frontend | PB-028 | Dashboard and weekly energy report
S11 | Personalization & Advanced Intelligence | Backend | PB-012, PB-022, PB-028 | Estimate task duration; Use history to improve future recommendations; Dashboard and weekly energy report
S11 | Personalization & Advanced Intelligence | ML | PB-012, PB-022 | Estimate task duration; Use history to improve future recommendations
S12 | Dashboard & Cross-Module Integration | Frontend | PB-003, PB-046 | Core application shell and dashboard; Integrate modules and validate end-to-end workflows
S12 | Dashboard & Cross-Module Integration | Backend | PB-003, PB-046 | Core application shell and dashboard; Integrate modules and validate end-to-end workflows
S12 | Dashboard & Cross-Module Integration | ML | PB-046 | Integrate modules and validate end-to-end workflows
S13 | Quality, Security & Evaluation | Frontend | PB-044, PB-045, PB-047 | Meet privacy, security, and performance requirements; Support offline viewing and later synchronization where feasible; Run functional, integration, usability, and performance testing
S13 | Quality, Security & Evaluation | Backend | PB-043, PB-044, PB-045, PB-047 | Establish baseline and evaluate intelligent components; Meet privacy, security, and performance requirements; Support offline viewing and later synchronization where feasible; Run functional, integration, usability, and performance testing
S13 | Quality, Security & Evaluation | ML | PB-043, PB-044, PB-047 | Establish baseline and evaluate intelligent components; Meet privacy, security, and performance requirements; Run functional, integration, usability, and performance testing
S14 | Final Stabilization & Delivery | Frontend | PB-046, PB-047 | Integrate modules and validate end-to-end workflows; Run functional, integration, usability, and performance testing
S14 | Final Stabilization & Delivery | Backend | PB-046, PB-047 | Integrate modules and validate end-to-end workflows; Run functional, integration, usability, and performance testing
S14 | Final Stabilization & Delivery | ML | PB-046, PB-047 | Integrate modules and validate end-to-end workflows; Run functional, integration, usability, and performance testing

## Project Phases
Phase | Sprints | Theme | Scope
Phase 1 | S01–S03 | Foundation & Scheduler | User foundation + scheduler core + schedule interaction
Phase 2 | S04–S05 | Human-State Signals | Energy + Attention
Phase 3 | S06–S07 | Decision Engine | Scoring + recommendations + explainability
Phase 4 | S08–S09 | Reactive Scheduling | Dynamic rescheduling + decision re-evaluation + notifications
Phase 5 | S10–S11 | External Inputs & Personalization | Calendar/email + advanced intelligence/history/reporting
Phase 6 | S12–S14 | Integration, Quality & Delivery | Dashboard integration + evaluation + testing + final documentation/demo

## Read Me
Topic | Guidance
Planning status | Baseline Agile Sprint Plan derived from PB-001–PB-048. It must be refined during Sprint Planning.
Sprint length | 2 weeks, as specified by the team.
Exact dates | Not hard-coded because the exact May 2027 submission date was not provided.
Planning horizon | 14 two-week slots are used as a baseline for the stated late-October-to-around-May horizon. This is not a claim about the exact final submission date.
Story Points | Not invented. The team should estimate them collaboratively during refinement/planning.
Team model | Every Sprint involves the team; Frontend, Backend, and ML work in parallel when the selected backlog items require those streams.
Scope source | Sprint items come from the existing Product Backlog only. No new product feature was added.
UML | UML is already complete and is not scheduled as work.
Agile rule | Move items between Sprints when real capacity, blockers, or Sprint Review results require it. The Product Backlog remains the source of truth.